## Student
Team: 1 |  | Topic: Covid-info
n.o | ID | Name | Role | Email | Role
1 | e20180328 | Hun Ravit | Leader/Support | hunravit2711@gmail.com | Reporter
2 | e20180248 | Han Kimhak | API/Support | hankimhak451@gmail.com | Design
3 | e20180033 | Bun Arya | Frontend/report | bunarya@yahoo.com | Frontend
4 | e20180044 | But Dalin | Frontend/Design | butdalin25@gmail.com | API
5 | e20180106 | Chheng Afa | Design/tester | afachheng@gmail.com | Tester
6 | e20180113 | Chhon Devit | Design/tester | chhondevit@gmail.com | Database
7 | e20180221 | Eiv Lina | Frontent/database | eivlina0221@gmail.com | Support
8 | e20180266 | Hel Sokheng | Report/Design | sokheng960567@gmail.com

## Information
Module | Feature | Sub Tasks | status | Response by | Start | Due on
Authentication | Register | Design UI | In progress | Designer | 15/03/2022 | 16/03/2022
|  | Create template | To Do | frontend | 16/03/2022 | 17/03/2022
|  | Create API | To Do | API | 16/03/2022 | 18/03/2022
| Login | Design UI | In progress | Designer | 15/03/2022 | 16/03/2022
|  | Create template | To Do | frontend | 16/03/2022 | 17/03/2022
|  | Create API | To Do | API | 16/03/2022 | 18/03/2022
Admin Dashboard | Visiting statistic / CMS
Product | Graph visualization (Bar chart)
Cambodia map visualization
General information (vacine, protection, ) of covid
Daily news related to covid
Dashboard | Homepage

## work
API
Feature | note | UI | Front-end | Build | Resource
Homepage |  | Already
Vaccine |  | N | Lina
Header and footer |  | Already | Dalin
Admin |  | N
Prevention |  | N | Sokheng
Symptom |  | Already | Afa
news |  | Already | Arya
Spread |  | Already | Devid
Map
Login and register |  | Already
Treatment

## Database
Login and Register | news